Title

Protocol for the development of a core outcome set for clinical trials of the management of Lyme disease

Version

V0.4 20-7-2021

Contents

Abstract	2

Background	3

Aims and objectives	3

Identifying existing knowledge	4

Scope of the core outcome set	4

Registration	4

Project oversight	4

Methods	4

Identification of outcomes	5

Quantitative systematic review	5

Review of ongoing registered trials	5

Qualitative systematic review	6

Outcome consolidation	6

Prioritisation of outcomes	6

Stakeholder Involvement	6

Online Delphi survey 	7

Consensus meeting	9

Ethical considerations	9

Dissemination	9

Administrative Information	9

Funding	10

Conflicts of interest	10

References	10

# Abstract

Background

Lyme disease (borreliosis) is the most prevalent tick borne disease in the United Stated and Western Europe. A UK review of available evidence for the management of Lyme disease concluded that the quality of evidence was low and that there was heterogeneity in the outcomes assessed. The development of a core outcome set for trials of the management of Lyme disease may help to address the issue of outcome heterogeneity and will also identify outcomes that are the most important to both clinicians and patients.

Methods

The core outcome set will be developed in three stages.  Systematic reviews of randomised controlled trials and the qualitative literature will identify a list of outcomes that will form the basis of a two round online Delphi survey.  The online Delphi survey will ask stakeholders to rate outcomes on their importance for inclusion in a core outcome set. The results of the Delphi survey will then be discussed and ratified at an online consensus meeting.

Discussion

Evidence synthesis for the management of Lyme disease has been hindered by heterogeneity in the outcomes measured and reported. The development of a core outcome set for trials of the management of Lyme disease, that represents outcomes importance to all stakeholders, aims to address this.

# Background

Lyme disease (borreliosis) is a tick-borne bacterial infection caused by the spirochetes of Lyme borrelia 1 . It is a public health concern in  Western Europe, the United States and Canada with incidence varying by country2. In the UK incidence  is estimated to be 2.7/100 000, with an additional 1000-2000 cases that are not confirmed by laboratory diagnosis 3. Comparatively in Southern Sweden the incidence rises to 464/100 0004.

Clinical manifestations of Lyme disease can be broadly grouped into early, localised infection typically manifesting as erythema-migrans (EM), early disseminated manifestations of multiple EM or late disseminated manifestations that include arthritis or acrodermatitis chronica atrophicans 5.

In 2018 the UK’s National Institute of Health and care Excellence (NICE), published guideline NG95 for Lyme disease. This guideline reviewed available evidence for the management of erythema migrans, neuroborreliosis, Lyme arthritis, Lyme carditis, non-specific symptoms related to Lyme disease, acrodermatitis chronica atrophicans, lymphocytoma, non-neurological ocular manifestations, and ongoing symptoms related to Lyme disease.  In general the quality of evidence was low, with heterogeneity in the outcomes and outcome definitions used. As a result the guideline committee recommended that a core outcome set (COS) be developed for the management of Lyme disease6.

A COS represents an agreed standardised set of outcomes that should be measured and reported, as a minimum, in all clinical research studies in a specific area of health care7. A COS may help to address the issues of outcome heterogeneity, allowing comparison of research findings to identify effective and safe treatments. The involvement of multiple stakeholder groups in the development of COS, including patients and health professionals, also increases the relevance of research and choice of outcomes.

This protocol outlines the development of a core outcome set for the management of Lyme disease in adults. This will provide a consensus recommendation on what outcomes should be measured in future research but further work will be needed to agree and recommend a measurement instrument for each of the outcomes in the COS.

# Aims and objectives

The aim of this study is to develop a COS for use in future clinical trials of the management of Lyme disease.

The specific objectives are to:

- Identify  outcomes measured in randomised clinical trials for the management of Lyme disease.

- Identify outcomes described in qualitative literature of patients’ lived experience of Lyme disease.

- Prioritise which outcomes patients, healthcare professionals and researchers think are critically important and should be included in a COS for the management of Lyme disease.

- Integrate the outcomes important to all stakeholder groups through a consensus process to agree a COS for clinical trials of the management of Lyme disease.

# Identifying existing knowledge

Prior to completing this project, a search of the Core Outcome Measures in Effectiveness Trials (COMET) Initiative database (on 3rd May 2021) revealed that there were no published or ongoing COS for the management of Lyme disease in adults.

# Scope of the core outcome set

This COS will be developed for use in clinical research of treatments for the management of Lyme disease in adults aged > 18 years.

Population:  Adults with Lyme disease (any diagnosis method).

Intervention: Any treatment of Lyme disease

Setting: Clinical research

# Registration

The Lyme-COS  Study has been registered with the Core Outcome Measures for Effectiveness Trials (COMET) database, reference www.comet-initiative.org/studies/details/1902

# Project oversight

A Study Management Group will be responsible for the day to day running of the study.

A Steering Committee comprised of clinicians, researchers and public contributors will advise on all stages of the project, providing feedback on the study protocol and list of outcomes to be considered in the consensus process and contributing to the dissemination of the online Delphi survey, the final consensus meeting and the dissemination of the COS.

# Methods

This protocol has been written using the COS-STAD (Core Outcome Set-STAndards for Development Recommendations 8 and the COS-STAP Statement (Core Outcome Set-STAndardised Protocol Items)9.

Study Design: The development of the COS will involve three key stages (figure 1): identification of outcomes, prioritisation of outcomes, online consensus meeting to review the COS.  An international Study Steering Committee (SSC) comprised of four health care professionals and four public contributors has been established. The remit of the SSC is to oversee the study, provide feedback on the study protocol and list of outcomes, contribute to the dissemination of the online Delphi survey and to contribute to the final consensus meeting and dissemination of the COS.

## Identification of outcomes

A list of outcomes, for presentation in an online Delphi survey, will be identified through data-based convergent synthesis10 involving a mixed studies systematic review of both quantitative and qualitative literature.

### Quantitative systematic review

Stokes et al  have previously developed an evidence map for Lyme disease in humans 11 which included a systematic review of the treatment and management of Lyme disease 12.  We will review the 78 studies included in this systematic review and update the search. The search strategy will be modified to include the Cochrane randomised control trial filter and will be date limited to identify new studies published since the initial search. The RCT filter will increase the specificity of the search in relation to the scope of the COS (appendix 1).

The references of any systematic or narrative reviews identified from the search strategy will be hand searched for relevant articles.

Abstracts and studies included in the previous systematic review will be screened for eligibility. Outcomes will be extracted from the methods and results sections of included literature. All outcomes will be recorded verbatim. Where reported the method of measurement will also be recorded.

Where a reported outcome is a composite outcome, the individual outcomes used in the composite will be recorded. Likewise, if a patient reported outcome measure (PROM) is used, then the domains measured by the PROM will be extracted.

Each outcome extracted will be categorized using the 38 core domains of the COMET taxonomy13

Verbatim outcomes within each category will then be reviewed and a generic outcome name applied and outcomes grouped if they are considered to represent the same outcome. For example, outcomes that are reported based on the measurement method for an outcome will be grouped.

### Review of ongoing registered trials

Ongoing trials that are actively recruiting or in follow up will be identified from a search of clincialtrials.gov and the WHO ICTRP. Outcomes will be identified from the registry entry and extracted verbatim.  Extracted outcomes will be categorised in the same way as those extracted from published RCTs.

### Qualitative systematic review

Outcomes relating to patients’ views and experiences of treatment for Lyme disease will be identified using a rapid review of qualitative studies. A search of the literature in MEDLINE, CINAHL Plus and ProQuest with no restrictions on date, will be performed.

The search terms, described in Appendix 2, comprise empirically tested qualitative methodological filters designed to identify qualitative research from the MEDLINE electronic database with the best balance of sensitivity and specificity 14.

Abstracts will be screened and the full text reviewed for articles meeting the following inclusion criteria: participants are adults with a diagnosis (any method) of Lyme disease, the focus is the management/treatment of Lyme disease and not diagnosis of Lyme disease, and qualitative methods (interviews and/or focus groups) have been used.

A narrative synthesis will be undertaken to identify text relevant to Lyme disease outcomes;  those outcomes will be categorised into the COMET taxonomy domains13.

### Outcome consolidation

Verbatim outcomes identified from the systematic review and the qualitative synthesis will be grouped by their COMET taxonomy domains.  The taxonomy comprises 38 core domains structured within five top level core areas: death, physiological/clinical, life impact, resource use, and adverse events.

Outcomes within each domain will be further reviewed and, where appropriate, grouped into a generic outcome. Following outcome categorisation and grouping, the Study Steering Committee will perform a batch check to verify that the outcomes have been appropriately categorised and grouped. The SSC will also be asked to confirm that there are no duplications within the generic outcomes and to comment on the wording and descriptive help text.

This list of outcomes generated is intended to be used in an online Delphi survey. To make the list manageable for Delphi participants, the SSC may suggest further grouping of outcomes, or the removal outcomes that have, for example, been measured in a single study or are considered to have low clinical or patient relevance.

The presentation of outcomes in the Delphi survey and their relevance to the stages of Lyme disease will also be considered.

## Prioritisation of outcomes

### Stakeholder Involvement

Participants will be recruited from the following stakeholder groups: people with Lyme disease, healthcare professionals involved in the management/treatment of patients with Lyme disease, researchers in the field. Healthcare policymakers will also be invited to take part.

People with Lyme disease will be eligible to take part irrespective of the method that they were diagnosed with Lyme disease.  We will ask participants whether their Lyme disease has resolved or if they have ongoing symptoms.

All participants will be asked to confirm the country in which they are based.

The Delphi survey will be distributed to patient and professional organisations relevant to Lyme disease and shared to mailing lists and on social media platforms.

The participant information sheet will be provided online, on the study homepage, prior to the registration page. Consent for participation in the online survey will be sought online prior to accessing the survey. Registration for the online Delphi survey will also include questions relating to eligibility.

There will be no restriction on the number of eligible participants in each stakeholder group completing the Delphi survey.

### Online Delphi survey

The list of outcomes identified from the systematic and qualitative reviews will be prioritised in a two round online Delphi survey delivered using DelphiManager software designed, hosted and delivered by the University of Liverpool. The Delphi approach involves administration of iterative surveys being administered to participants, with anonymised feedback of the results provided after each round. This approach gives equal influence to all participants, facilitates international contribution and offers a mechanism for reconciling differences of opinion7,15,16.

Consideration will be given to how best to group outcomes for presentation in the online Delphi survey. For example, these may be grouped into the areas of mortality, physiological/clinical, life impact, resource use and adverse events. The grouping of outcomes into domains for presentation in the Delphi will be reviewed by the SSC prior to Delphi launch.

Domains will be presented in the online Delphi survey in a random order for each participant unless the grouping of outcomes means that a logical order should be followed.

Online Delphi survey  participants will be asked to rate each outcome using the Grading of Recommendations, Assessment, Development and Evaluations (GRADE) nine point Likert scale.17 In the Delphi process the scale will be presented in the format 1 to 9, with 1 to 3 labelled ‘not that important’, 4 to 6 labelled ‘important but not critical’ and 7 to 9 labelled ‘critical’. An option of “unable to rate” will also be included together with an option to add a comment on each outcome about the reasons for their score.

The outcomes list will be written in plain language and additional help text developed for each outcome.

The Delphi survey will have two rounds. At the end of round 1, participants will be able to suggest additional outcomes they think are important but not already included on the list. Additional outcomes suggested will be summarised and reviewed by the SSC. Any new outcomes or amendments to the descriptions of existing outcomes will be added to round 2 of the Delphi survey.

Results from round 1 of the Delphi survey will be summarised and presented graphically in round 2 as the percentage of each stakeholder group who have given each rating. All outcomes scored in round 1 will be retained for round 2. Participants will be able to view the grouped responses of other stakeholders together with their own score in round 1. In round 2 participants will be asked to consider this information and to re-rate the outcome using the same 1-9 scale. Participants may choose to change their score or to keep it the same. New outcomes identified from free text responses in round 1 will be presented in round 2 alongside the verbatim text that led to the outcome. Participants will be asked to rate these new outcomes.

Round 2 responses will be summarised using descriptive statistics and a predefined definition of consensus (Table 2). Participants will be encouraged to provide a response (a rating or ‘unable to rate’) for each outcome. Responses will be included in the analysis if a participant assesses more than 80% of the outcomes. However, this approach will be reviewed with the SSC based on the response rate to round 1.

Table 2. Definition of consensus

| Consensus Classification | Description | Definition |
| --- | --- | --- |
| Consensus in | Consensus that outcome should be included in the core outcome set | 80% or more participants, in each stakeholder group, scoring as 7-9 AND <15% participants, in each stakeholder group, scoring as 1-3 |
| Consensus out | Consensus that outcome should not be included in the core outcomes set | 50% or fewer participants scoring 7-9 in each stakeholder group. |
| No consensus | Uncertainty about importance of outcome | Anything else |

Attrition

To minimise attrition within and between rounds automated reminder emails will be sent to registered participants who have yet to complete the current round of the Delphi survey. At least two reminder emails will be scheduled for each round with additional reminders determined by the response rate and any extensions to the duration of the round.

Attrition bias will be assessed by visually comparing the distribution of mean R1 scores for participants completing R1 only and participants completing both R1 and R2 for each stakeholder group.

### Consensus meeting

The results of the Delphi survey will be discussed at an online consensus meeting chaired by an independent facilitator. A sample of participants who completed both rounds of the Delphi survey and expressed an interest in attending the consensus meeting will be invited to attend, ensuring similar numbers from each stakeholder group.  It is anticipated that a maximum of 30 participants will attend the online consensus meeting, distributed equally across clinician, researcher and patient stakeholder groups completing the online Delphi survey.

The consensus meeting will ratify the results of the Delphi survey and confirm the outcomes that have met the definition of inclusion or exclusion from the COS after round 2.

Outcomes that have no consensus at the end of round 2 will be discussed and rated, for inclusion in the COS.  Outcomes that have been rated as “consensus in” by at least one of the stakeholder groups will be prioritised for discussion and rating at the consensus meeting.

# Ethical considerations

Ethical approval for the online Delphi survey and the consensus meeting will be sought from the University of Liverpool Research Ethics Committee. Participant information will be provided online on the Delphi home page as the homepage text, this page is available prior to the registration/consent page.

Consent for participation in the online Delphi will be recorded online and will be mandatory prior to accessing the outcome rating section of the survey. Participants are free to withdraw from the survey at any time without giving reason, partial responses will not be considered as withdrawal and data will be used unless participants specifically ask for their data to be withdrawn from the analysis. For the online consensus meeting, participants of the Delphi, interested in attending, will consent to being contacted with further information at the end of round 2. A PDF information sheet will be emailed to participants and attendance at the online consensus meeting considered to be consent to participate.

# Dissemination

Following completion of the project, findings will be submitted for publication in a peer reviewed journal. Results will be presented following the COS-STAR reporting guideline18.  A plain language summary of the findings will also be fed back to all participants.

# Administrative Information

## Funding

This project has been funded by Lyme Disease Action, a UK charity. Lyme Disease Action has representatives in the SSC. Any decisions around publication or dissemination of the results will be made in conjunction with the SSC and will not be the sole decision of the funder.

## Conflicts of interest

None

# References

1.	Stanek G, Wormser GP, Gray J, Strle F. Lyme borreliosis. Lancet (London, England). 2012;379(9814):461-473.

2.	Hubálek Z. Epidemiology of Lyme Borreliosis. Current Problems in Dermatology. Vol 372009:31-50.

3.	England PH. Lyme disease epidemiology and surveillance. 2018.

4.	Sykes RA, Makiello P. An estimate of Lyme borreliosis incidence in Western Europe†. Journal of public health (Oxford, England). 2017;39(1):74-81.

5.	Borchers AT, Keen CL, Huntley AC, Gershwin ME. Lyme disease: A rigorous review of diagnostic criteria and treatment. J. Autoimmun. 2015;57:82-115.

6.	Excellence NIfHaC. NG95/1: Core outcome set for studies of management of Lyme disease:- Can a core outcome set be developed for clinical trials of management of Lyme disease? 2018; https://www.nice.org.uk/about/what-we-do/research-and-development/research-recommendations/NG95/1. Accessed 6-5-2021.

7.	Williamson PR, Altman DG, Bagley H, et al. The COMET Handbook: version 1.0. Trials. 2017;18(3):280.

8.	Kirkham JJ, Davis K, Altman DG, et al. Core Outcome Set-STAndards for Development: The COS-STAD recommendations. PLOS Medicine. 2017;14(11):e1002447.

9.	Kirkham JJ, Gorst S, Altman DG, et al. Core Outcome Set-STAndardised Protocol Items: the COS-STAP Statement. Trials. 2019;20(1):116.

10.	Hong QN, Pluye P, Bujold M, Wassef M. Convergent and sequential synthesis designs: implications for conducting and reporting systematic reviews of qualitative and quantitative evidence. Systematic Reviews. 2017;6(1):61.

11.	Stokes G BL, Sutcliffe K, Dickson K, Brunton G, Burchett H, Jones-Diette J, Hinds, K, Khatwa M, Lorenc T, Khouja C, Walker R, Rojas-Garcia A, Rees R, Harden M, Stansfield, C, Sowden A, Thomas J Systematic Evidence Map of Research on Lyme disease in Humans. London EPPI-Centre, Social Science Research Unit, UCL Institute of Education,

University College London.;2017.

12.	Sutcliffe K SA, Burchett H, Stansfield C, Harden M, Thomas J. Patient, clinician and researcher experiences of the treatment and management of Lyme disease: a systematic review. London EPPI-Centre, Social Science Research Unit, UCL Institute of Education, University College London;2017.

13.	Dodd S, Clarke M, Becker L, Mavergames C, Fish R, Williamson PR. A taxonomy has been developed for outcomes in medical research to help improve knowledge discovery. Journal of Clinical Epidemiology. 2018;96:84-92.

14.	Wong SS, Wilczynski NL, Haynes RB. Developing optimal search strategies for detecting clinically relevant qualitative studies in MEDLINE. Studies in health technology and informatics. 2004;107(Pt 1):311-316.

15.	Sinha IP, Smyth RL, Williamson PR. Using the Delphi technique to determine which outcomes to measure in clinical trials: recommendations for the future based on a systematic review of existing studies. PLoS medicine. 2011;8(1):e1000393.

16.	Jones J, Hunter D. Consensus methods for medical and health services research. BMJ (Clinical research ed.). 1995;311(7001):376-380.

17.	Guyatt GH, Oxman AD, Kunz R, et al. GRADE guidelines: 2. Framing the question and deciding on important outcomes. J Clin Epidemiol. 2011;64(4):395-400.

18.	Kirkham JJ, Gorst S, Altman DG, et al. Core Outcome Set-STAndards for Reporting: The COS-STAR Statement. PLoS Med. 2016;13(10):e1002148.

Appendix 1

Search strategy for RCTs (modified from Sutcliffe et al 201712).

Search date 16-2-2021

MEDLINE (via Ovid) search strategy

1 exp Lyme Disease/ (11260)

2 (lyme or lymes or lyme's).ti,ab. (11966)

3 borreliosis.ti,ab. (3817)

4 neuroborreliosis.ti,ab. (1306)

5 (borrelia$ adj2 arthritis).ti,ab. (43)

6 (erythema adj2 migrans).ti,ab. (1718)

7 1 or 2 or 3 or 4 or 5 or 6 (15158)

8 exp Borrelia burgdorferi Group/ (7543)

9 (borrelia adj (burgdorferi or afzelii or garinii)).ti,ab. (8663)

10 (b adj (burgdorferi or afzelii or garinii)).ti,ab. (5091)

11 8 or 9 or 10 (10559)

12 7 or 11 (17117)

13 exp animals/ not humans/ (4788227)

14 12 not 13 (13675)

15 limit 14 to yr=”2017-Current” (2249))  (all studies with date limit)

Add RCT filter

16  randomized controlled trial.pt. (533857)
17  controlled clinical trial.pt. (94217)
18 randomized.ab. (523882)
19 placebo.ab.( 218964)
20 drug therapy.fs. (2332370)
21 randomly.ab. (359750)
22 trial.ab.(556250)
23 groups.ab.(2208461)
24 1 or 2 or 3 or 4 or 5 or 6 or 7 or 8 (5032751)

25 24 AND 15 (439) (with RCT filter) (427 when duplicates removed)

Appendix 2 –

Search strategy for qualitative studies using best specificity (small decrease in specificity with a large increase in sensitivity14)

MEDLINE (via Ovid) search strategy

1 exp Lyme Disease/ (11109)

2 (lyme or lymes or lyme's).ti,ab. (11854)

3 borreliosis.ti,ab. (3790)

4 neuroborreliosis.ti,ab. (1289)

5 (borrelia$ adj2 arthritis).ti,ab. (42)

6 (erythema adj2 migrans).ti,ab. (1699)

7 1 or 2 or 3 or 4 or 5 or 6 (15019)

8 exp Borrelia burgdorferi Group/ (7447)

9 (borrelia adj (burgdorferi or afzelii or garinii)).ti,ab. (8585)

10 (b adj (burgdorferi or afzelii or garinii)).ti,ab. (5064)

11 8 or 9 or 10 (10466)

12 7 or 11 (16958)

13 exp animals/ not humans/ (4788227)

14 12 not 13 (13583)

15 Interviews.mp,pt (224832)

16 qualitative.mp (274768)

17 experiences.tw (218976)

18 15 OR 16 OR 17 (571945)

14 and 18 (87) (qualitative studies with no date range)